## Project schedule
| PROJECT: RFM (Recency, Frequency, and Monetary) Analysis dan Segmentasi Pelanggan pada CV Bali Raspberry |  |  |  |  | Project start: | [7 empty] | 2024-04-03
[6 empty] | Display week: | [7 empty] | 1
[6 empty] | APRIL | [27 empty] | MAY | [30 empty] | JUNE | [29 empty] | JULY
| TASK | PROGRESS | START | END | time axis 2024-04-03 to 2024-07-10
 | time axis 2024-04-03 to 2024-07-10
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
RFM Analysis and Clustering
| Analytic Approach | 100% | 2024-04-06 | 2024-04-20 | 15
| Data Collection | 100% | 2024-04-08 | 2024-04-29 | 22
| Data Preparation | 50% | 2024-04-29 | 2024-05-06
| RFM Analysis | 20% | 2024-05-09 | 2024-05-23 | 15
| Clustering Customers | 20% | 2024-05-09 | 2024-05-23
Visualization Project
| Define the Requirements | 0% | 2024-05-09 | 2024-05-16 | 8
| Prototype | 0% | 2024-05-16 | 2024-05-30 | 15
| Create Web | 0% | 2024-05-23 | 2024-06-27 | 36
Reporting
| Making Report | 30% | 2024-06-27 | 2024-07-04 | 8
| Making Presentation | 0% | 2024-06-28 | 2024-07-10 | 13